## Issues
Key | Summary | Type | Status | Priority | Assignee | Story Points | Created | Updated | Resolved | Sprint | Labels | Reopened
SAKURA-1 | Implement product search API | Story | Done | Medium | Tanaka | 8 | 2026-05-04 | 2026-05-18 | 2026-05-18 | Sprint 9 |  | No
SAKURA-2 | Build cart page UI | Story | Done | Medium | Tanaka | 5 | 2026-05-04 | 2026-05-19 | 2026-05-19 | Sprint 9 |  | No
SAKURA-3 | Checkout API integration | Story | Done | Medium | Tanaka | 8 | 2026-05-04 | 2026-05-20 | 2026-05-20 | Sprint 9 |  | No
SAKURA-4 | Product detail page | Task | Done | Medium | Suzuki | 3 | 2026-05-04 | 2026-05-17 | 2026-05-17 | Sprint 9 |  | No
SAKURA-5 | Wishlist feature | Story | Done | Medium | Tanaka | 5 | 2026-05-04 | 2026-05-21 | 2026-05-21 | Sprint 9 |  | No
SAKURA-6 | Order history screen | Task | Done | Medium | Nguyen | 3 | 2026-05-04 | 2026-05-16 | 2026-05-16 | Sprint 9 |  | No
SAKURA-7 | Coupon code validation | Task | Done | Medium | Pham | 2 | 2026-05-04 | 2026-05-19 | 2026-05-19 | Sprint 9 |  | No
SAKURA-8 | Email receipt template | Task | Done | Medium | Sato | 2 | 2026-05-04 | 2026-05-20 | 2026-05-20 | Sprint 9 |  | No
SAKURA-9 | Payment gateway integration | Story | In Progress | Medium | Suzuki | 8 | 2026-05-05 | 2026-05-20 |  | Sprint 9 |  | No
SAKURA-10 | Inventory sync service | Story | In Progress | Medium | Nguyen | 8 | 2026-05-05 | 2026-05-20 |  | Sprint 9 |  | No
SAKURA-11 | Address book management | Task | In Progress | Medium | Pham | 3 | 2026-05-05 | 2026-05-20 |  | Sprint 9 |  | No
SAKURA-13 | Shipping cost calculator | Task | In Progress | Medium | Sato | 5 | 2026-05-05 | 2026-05-20 |  | Sprint 9 |  | No
SAKURA-14 | Product recommendation widget | Story | In Progress | Medium | Suzuki | 5 | 2026-05-05 | 2026-05-20 |  | Sprint 9 |  | No
SAKURA-16 | Admin order dashboard | Story | In Progress | Medium | Nguyen | 8 | 2026-05-05 | 2026-05-20 |  | Sprint 9 |  | No
SAKURA-17 | Refund processing flow | Task | In Progress | Medium | Pham | 5 | 2026-05-05 | 2026-05-20 |  | Sprint 9 |  | No
SAKURA-18 | Multi-currency display | Task | In Progress | Medium | Sato | 3 | 2026-05-05 | 2026-05-20 |  | Sprint 9 |  | No
SAKURA-19 | Guest checkout flow | Story | In Progress | Medium | Suzuki | 5 | 2026-05-05 | 2026-05-20 |  | Sprint 9 |  | No
SAKURA-21 | Loyalty points engine | Story | In Progress | Medium | Nguyen | 8 | 2026-05-05 | 2026-05-20 |  | Sprint 9 |  | No
SAKURA-22 | Performance load testing | Task | To Do | Medium | Pham | 5 | 2026-05-10 | 2026-05-12 |  | Sprint 9 |  | No
SAKURA-23 | Accessibility audit | Task | To Do | Medium | Sato | 3 | 2026-05-10 | 2026-05-12 |  | Sprint 9 |  | No
SAKURA-24 | SEO metadata pass | Task | To Do | Medium | Suzuki | 2 | 2026-05-10 | 2026-05-12 |  | Sprint 9 |  | No
SAKURA-34 | Final UAT preparation | Task | To Do | Medium | Nguyen | 3 | 2026-05-10 | 2026-05-12 |  | Sprint 9 |  | No
SAKURA-12 | Configure CDN caching rules | Task | Done | Medium | Sato | 3 | 2026-05-06 | 2026-05-19 | 2026-05-19 | Sprint 9 |  | No
SAKURA-15 | Order confirmation webhook | Story | In Progress | Medium | Suzuki | 5 | 2026-05-05 | 2026-05-20 |  | Sprint 9 |  | No
SAKURA-20 | Tax calculation module | Story | In Progress | Medium | Pham | 8 | 2026-05-04 | 2026-05-21 |  | Sprint 9 |  | No
SAKURA-30 | Spike: evaluate GraphQL gateway | Task | In Progress | Medium | Tanaka | 3 | 2026-05-12 | 2026-05-20 |  | Sprint 9 |  | No
SAKURA-25 | Cart total miscalculates with coupon | Bug | In Progress | High | Pham | 2 | 2026-04-20 | 2026-04-22 |  | Sprint 9 |  | No
SAKURA-26 | Checkout crashes on Safari | Bug | In Progress | Severity-1 | Suzuki | 3 | 2026-05-17 | 2026-05-21 |  | Sprint 9 |  | No
SAKURA-27 | Search returns stale results | Bug | In Progress | Medium | Nguyen | 2 | 2026-05-08 | 2026-05-20 |  | Sprint 9 |  | Yes
SAKURA-28 | Wishlist item duplicates | Bug | In Progress | Medium | Sato | 2 | 2026-05-08 | 2026-05-20 |  | Sprint 9 |  | Yes
SAKURA-29 | Address validation false negative | Bug | In Progress | Medium | Pham | 2 | 2026-05-08 | 2026-05-20 |  | Sprint 9 |  | Yes
SAKURA-31 | Footer link 404 | Bug | Done | Low | Sato | 1 | 2026-05-11 | 2026-05-16 | 2026-05-16 | Sprint 9 |  | No
SAKURA-32 | Image lazy-load flicker | Bug | Done | Low | Suzuki | 1 | 2026-05-11 | 2026-05-18 | 2026-05-18 | Sprint 9 |  | No
SAKURA-33 | Currency symbol misaligned | Bug | Done | Low | Nguyen | 1 | 2026-05-11 | 2026-05-20 | 2026-05-20 | Sprint 9 |  | No
SAKURA-35 | Coupon field accepts whitespace | Bug | In Progress | Low | Pham | 1 | 2026-05-15 | 2026-05-20 |  | Sprint 9 |  | No
SAKURA-36 | Slow first paint on category page | Bug | To Do | Medium | Sato | 2 | 2026-05-18 | 2026-05-19 |  | Sprint 9 |  | No

## Sprints
Sprint | Start | End | Committed SP | Completed SP
Sprint 7 | 2026-04-17 | 2026-04-30 | 40 | 24
Sprint 8 | 2026-05-01 | 2026-05-14 | 45 | 27
Sprint 9 | 2026-05-15 | 2026-05-28 | 48 | 31