## Issues
Key | Summary | Type | Status | Priority | Assignee | Story Points | Created | Updated | Resolved | Sprint | Labels | Reopened
ATLAS-1 | Wave 2 payment cutover plan | Story | Done | High | Sato | 8 | 2026-05-20 | 2026-06-02 | 2026-06-02 | Atlas Sprint 12 |  | No
ATLAS-2 | Warehouse sync refactor | Story | In Progress | High | Tanaka | 13 | 2026-05-18 | 2026-06-07 |  | Atlas Sprint 12 | critical-path | No
ATLAS-3 | Cost dashboard EVM feed | Task | Done | Medium | Nguyen | 5 | 2026-05-22 | 2026-06-03 | 2026-06-03 | Atlas Sprint 12 | evm | No
ATLAS-4 | Approved Change Request 17 pricing update | Story | In Progress | High | Suzuki | 8 | 2026-05-25 | 2026-06-06 |  | Atlas Sprint 12 | change-request | No
ATLAS-5 | SIT defect batch A | Bug | In Progress | Severity-1 | Pham | 3 | 2026-05-28 | 2026-06-07 |  | Atlas Sprint 12 | sit | No
ATLAS-6 | Legacy order migration rehearsal | Task | Done | Medium | Tanaka | 5 | 2026-05-19 | 2026-06-01 | 2026-06-01 | Atlas Sprint 12 | migration | No
ATLAS-7 | Carrier contract mapping | Task | In Progress | Medium | Nguyen | 5 | 2026-05-24 | 2026-06-07 |  | Atlas Sprint 12 |  | Yes
ATLAS-8 | Customer steering deck numbers | Task | Done | Medium | Sato | 3 | 2026-05-30 | 2026-06-04 | 2026-06-04 | Atlas Sprint 12 | evm | No

## Sprints
Sprint | Start | End | Committed SP | Completed SP
Atlas Sprint 10 | 2026-04-27 | 2026-05-10 | 48 | 37
Atlas Sprint 11 | 2026-05-11 | 2026-05-24 | 52 | 34
Atlas Sprint 12 | 2026-05-25 | 2026-06-07 | 56 | 31