## WBS
Task ID | Phase | Task Name | Planned Start | Planned End | Planned MM | Planned % | Owner | Jira Key
A1-T01 | Wave 1 | Migration readiness | 2026-04-01 | 2026-05-15 | 20 | 100 | Sato
A2-T01 | Wave 2 SIT | Payment cutover plan | 2026-05-18 | 2026-06-03 | 18 | 95 | Sato | ATLAS-1
A2-T02 | Wave 2 SIT | Warehouse sync refactor | 2026-05-20 | 2026-06-04 | 22 | 90 | Tanaka | ATLAS-2
A2-T03 | Wave 2 SIT | Cost dashboard EVM feed | 2026-05-22 | 2026-06-02 | 10 | 100 | Nguyen | ATLAS-3
A2-T04 | Wave 2 SIT | Pricing CR implementation | 2026-05-25 | 2026-06-05 | 16 | 75 | Suzuki | ATLAS-4
A2-T05 | Wave 2 SIT | Migration rehearsal | 2026-05-19 | 2026-06-01 | 12 | 100 | Tanaka | ATLAS-6
A3-T01 | UAT | Steering deck numbers | 2026-05-30 | 2026-06-04 | 6 | 100 | Sato | ATLAS-8
A3-T02 | UAT | Carrier contract mapping | 2026-05-24 | 2026-06-02 | 8 | 85 | Nguyen | ATLAS-7