## Issues
Key | Summary | Type | Status | Priority | Assignee | Story Points | Created | Updated | Resolved | Sprint | Labels | Reopened
BEACON-1 | Partner portal UAT checklist | Task | Done | Medium | Ito | 5 | 2026-05-20 | 2026-06-02 | 2026-06-02 | Beacon Sprint 5 |  | No
BEACON-2 | API certification package | Story | In Progress | High | Yamada | 8 | 2026-05-24 | 2026-06-07 |  | Beacon Sprint 5 | external-dependency | No
BEACON-3 | Approved Change Request 04 reporting tweak | Task | In Progress | Medium | Nguyen | 3 | 2026-05-29 | 2026-06-06 |  | Beacon Sprint 5 | change-request | No
BEACON-4 | Dashboard widget styling | Task | Done | Low | Ito | 3 | 2026-05-26 | 2026-06-03 | 2026-06-03 | Beacon Sprint 5 |  | No
BEACON-5 | Regression defect in PDF export | Bug | In Progress | High | Sato | 2 | 2026-05-31 | 2026-06-07 |  | Beacon Sprint 5 | uat | No
BEACON-6 | Budget narrative alignment | Task | Done | Medium | Nguyen | 2 | 2026-05-28 | 2026-06-04 | 2026-06-04 | Beacon Sprint 5 | evm | No

## Sprints
Sprint | Start | End | Committed SP | Completed SP
Beacon Sprint 3 | 2026-04-27 | 2026-05-10 | 18 | 16
Beacon Sprint 4 | 2026-05-11 | 2026-05-24 | 20 | 14
Beacon Sprint 5 | 2026-05-25 | 2026-06-07 | 22 | 12