## WBS
Task ID | Phase | Task Name | Planned Start | Planned End | Planned MM | Planned % | Owner | Jira Key
B1-T01 | Foundation | Partner portal baseline | 2026-04-20 | 2026-05-20 | 5 | 100 | Ito
B2-T01 | Certification | API certification package | 2026-05-24 | 2026-06-04 | 8 | 90 | Yamada | BEACON-2
B2-T02 | Certification | Reporting CR update | 2026-05-29 | 2026-06-03 | 3 | 100 | Nguyen | BEACON-3
B3-T01 | UAT | Partner portal UAT checklist | 2026-05-20 | 2026-06-02 | 4 | 100 | Ito | BEACON-1
B3-T02 | UAT | PDF export regression fix | 2026-05-31 | 2026-06-05 | 2.5 | 80 | Sato | BEACON-5
B3-T03 | UAT | Budget narrative alignment | 2026-05-28 | 2026-06-04 | 1.5 | 100 | Nguyen | BEACON-6