## WBS
Task ID | Phase | Task Name | Planned Start | Planned End | Planned MM | Planned % | Owner | Jira Key
P1-T01 | Phase 1 Design | Requirements finalization | 2026-04-01 | 2026-04-10 | 1.5 | 100 | Nguyen
P1-T02 | Phase 1 Design | UI/UX wireframes | 2026-04-08 | 2026-04-20 | 2 | 100 | Sato
P1-T03 | Phase 1 Design | Technical architecture | 2026-04-15 | 2026-04-30 | 1.5 | 100 | Tanaka
P2-T04 | Phase 2 Development | Product search API | 2026-05-01 | 2026-05-18 | 2 | 90 | Tanaka | SAKURA-1
P2-T05 | Phase 2 Development | Tax calculation module | 2026-05-05 | 2026-05-18 | 1.5 | 85 | Pham | SAKURA-20
P2-T06 | Phase 2 Development | Payment gateway integration | 2026-05-06 | 2026-05-26 | 2.5 | 80 | Suzuki | SAKURA-9
P2-T07 | Phase 2 Development | Inventory sync service | 2026-05-08 | 2026-05-27 | 2 | 80 | Nguyen | SAKURA-10
P2-T08 | Phase 2 Development | Cart and checkout | 2026-05-04 | 2026-05-22 | 2.5 | 88 | Tanaka | SAKURA-3
P2-T09 | Phase 2 Development | Order confirmation webhook | 2026-05-05 | 2026-05-25 | 1.5 | 82 | Suzuki | SAKURA-15
P3-T10 | Phase 3 Testing | Performance load testing | 2026-05-25 | 2026-06-08 | 2 | 0 | Pham | SAKURA-22
P3-T11 | Phase 3 Testing | Accessibility audit | 2026-05-27 | 2026-06-05 | 1 | 0 | Sato | SAKURA-23
P3-T12 | Phase 3 Testing | User acceptance testing | 2026-06-01 | 2026-06-12 | 1.5 | 0 | Nguyen | SAKURA-34